## Cover Sheet
Pilot 2 |  | New Codington Festival Online
Entry/Exit Criteria Template
Version: 1.0
This document sets out what is required to start a stage and when the stage is considered complete on the New Codington Festival Online project. Each tab lists the exit and entry criteria together. The entry criteria are the states and conditions of project outcomes from the previous stage that must be satisfied before beginning the next stage. The exit criteria provide control of the project milestone completion. Exit/Entry criteria confirm if the required tasks and steps were satisfactorily completed; the required deliverables completed, reviewed, and received sign-off before the stage is considered complete and the project is ready for transition.

## Design - Build
Stage Entry and Exit Criteria
Role 1: Project Sponsor | Michael Stevens |  |  | Sign-off date: | Review not started
Role 2: Project Manager | Paul Cochrane |  |  | Sign-off date: | Review not started
Role 3: Technical Architect | David Hughes |  |  | Sign-off date: | Review not started
Role 4: Test Manager | Helen Smyth |  |  | Sign-off date: | Review not started
Role 5: Development Manager | Richard Lawrence |  |  | Sign-off date: | Review not started
Role 6: Team Lead |  |  |  | Sign-off date: | Review not started
Role 7: Developer |  |  |  | Sign-off date: | Review not started
Criteria per Development Phase |  | Status | Comments |  |  | Evaluator
Design Exit/Build Application Entry
The majority of application designs have been completed and build/component test can begin for completed designs that do not have dependencies on uncompleted designs.
Test plans for product test, performance test, and user acceptance test are complete.
Test plans for assembly test have started.
All appropriate design phase deliverables have been peer reviewed by resources with the appropriate skills to ensure the overall design is complete and consistent with minimal risk of rework in future phases.
The design deliverables have been reviewed for technical feasibility, adherence to standards, alignment with the architecture and for quality related requirements such as flexibility, performance, reliability, and usability.
All the appropriate design phase deliverables have been checked into the program's version control tools and baselined.
All outstanding issues and risks have been reviewed by the project team and stakeholders and proper mitigation plans are in place so the project can proceed to the subsequent phase with minimal chance of rework.
The approach to ramp up the build/component test team exists.
Some team members from the design phase are ready to transition to the build/component test phase and the approach to ramping up knowledge of new resources has been established.

## Build - Unit Test
Stage Entry and Exit Criteria
Role 1: Project Sponsor | Michael Stevens |  |  | Sign-off date: | Review not started
Role 2: Project Manager | Paul Cochrane |  |  | Sign-off date: | Review not started
Role 3: Technical Architect | David Hughes |  |  | Sign-off date: | Review not started
Role 4: Test Manager | Helen Smyth |  |  | Sign-off date: | Review not started
Role 5: Development Manager | Richard Lawrence |  |  | Sign-off date: | Review not started
Role 6: Team Lead |  |  |  | Sign-off date: | Review not started
Role 7: Developer |  |  |  | Sign-off date: | Review not started
Criteria per Development Phase |  | Status | Comments |  |  | Evaluator
Build Exit/Unit Test Application Entry
Complete the Test Conditions and Scenarios and Test Cycle Control Sheet deliverables.
Ensure the text for the cycle description is understandable by the reviewer.
Ensure all cycles test an appropriate number of conditions.
Write conditions in functional terms.
Make sure conditions thoroughly test the component function.
Cross-reference conditions and test cycles.
Identify the functional test conditions.
Identify any conditions that cannot be tested.
Logically group conditions into test cycles.
Define white box test conditions.
Augment test conditions if necessary.
Ensure the expected results are easy to understand by the executor.
Cross-reference test cycles and test conditions.
Ensure the executor can understand what characteristics the data needs in order to re-execute; all output references demonstrate conditions being tested.
Define the test configuration: stub programs and job streams.
Cross-reference the input data, output data, and test conditions.
Ensure all input data tests match the specified conditions.
Document the expected results.
Create the scripts.
Document input data and output data.
Document test configuration.
Ensure the test is repeatable based on the information given.
Write scripts at the appropriate level for executors.
Ensure scripts are modular (normal, error conditions, extremes).
Ensure scripts have a logical flow.
Test the following: Boolean logic, close-outs (process ends without errors), cross-field validation, cross-references, product initialization, input/output, SQL, intermediate updates, internal sorts, invalid entries, locking, loops, maximum and minimum values, merged files, and status conditions.
Make calculations only with valid numeric data.
Ensure high-order truncation in receiving numeric fields does not occur.
Develop and represent percentages and variances properly.
Apply rounding rules correctly.
Test the “divide by zero” function. The module does not terminate because it attempts to divide by zero; the error is caught and the appropriate error message prints.
Handle negative and positive numbers properly.
Ensure called module linkage works correctly: make each different type of possible call to the module; detect and handle invalid calling conditions; if optional records are passed, include testing with and without them; test the values in each message field.
Test each error condition that the module is supposed to handle.
Detect errors and prevent them from causing further error.
Ensure that the controls reflect the errors caught.
Demonstrate all planned fatal errors, at least by code review.

## Unit Test - Assembly Test
Stage Entry and Exit Criteria
Role 1: Project Sponsor | Michael Stevens |  |  | Sign-off date: | Review not started
Role 2: Project Manager | Paul Cochrane |  |  | Sign-off date: | Review not started
Role 3: Technical Architect | David Hughes |  |  | Sign-off date: | Review not started
Role 4: Test Manager | Helen Smyth |  |  | Sign-off date: | Review not started
Role 5: Development Manager | Richard Lawrence |  |  | Sign-off date: | Review not started
Role 6: Team Lead |  |  |  | Sign-off date: | Review not started
Role 7: Developer |  |  |  | Sign-off date: | Review not started
Criteria per Development Phase |  | Status | Comments |  |  | Evaluator
Unit Test Exit/Assembly Test Application Entry
Document the Unit Test actual results.
Document all Unit Test resolved problems.
Document any problems remaining to be resolved.
Ensure the actual results show proof of testing.
Cross-reference the test cycles and conditions.
Ensure the flow of the test is clear to the reviewer.
Ensure all conditions are successfully tested.
Ensure the programming supervisor reviews the component test packet following the test.
Update test cycles and test conditions with testing status.
Check the component into version control.
Update the status of the component.
Determine whether the module performs all aspects of function as defined.
Ensure the peer reviewer can gain a basic understanding of the component from the documentation.

## Assembly Test - Product Test
Stage Entry and Exit Criteria
Role 1: Project Sponsor | Michael Stevens |  |  | Sign-off date: | Review not started
Role 2: Project Manager | Paul Cochrane |  |  | Sign-off date: | Review not started
Role 3: Technical Architect | David Hughes |  |  | Sign-off date: | Review not started
Role 4: Test Manager | Helen Smyth |  |  | Sign-off date: | Review not started
Role 5: Development Manager | Richard Lawrence |  |  | Sign-off date: | Review not started
Role 6: Team Lead |  |  |  | Sign-off date: | Review not started
Role 7: Developer |  |  |  | Sign-off date: | Review not started
Criteria per Development Phase |  | Status | Comments |  |  | Evaluator
Assembly Test Exit/Product Test Application Entry
All "assembly test" phase deliverables tracked in the project's customized AP201 Requirements and Traceability have been completed, reviewed, and signed-off by the appropriate resources.
The product test environment has been setup and configured.
All application components have been built and component tested.
Majority of application components have been assembly tested.
Product test can begin for completed application components that do not have dependencies on uncompleted assembly tests.
The assembly tests have been successfully validated against the functional designs to ensure the proper function of integrated application components.
All appropriate "assembly test" phase deliverables have been peer reviewed by resources with the appropriate skills to ensure the overall design is complete and consistent with minimal risk of rework in future phases.
All appropriate "assembly test" phase deliverables have been checked into the program's version control tools and baselined.
All outstanding issues and risks have been reviewed by the project team and stakeholders and proper mitigation plans are in place so the project can proceed to the subsequent phase with minimal chance of rework.

## Product Test - UAT
Stage Entry and Exit Criteria
Role 1: Project Sponsor | Michael Stevens |  |  | Sign-off date: | Review not started
Role 2: Project Manager | Paul Cochrane |  |  | Sign-off date: | Review not started
Role 3: Technical Architect | David Hughes |  |  | Sign-off date: | Review not started
Role 4: Test Manager | Helen Smyth |  |  | Sign-off date: | Review not started
Role 5: Development Manager | Richard Lawrence |  |  | Sign-off date: | Review not started
Role 6: Team Lead |  |  |  | Sign-off date: | Review not started
Role 7: Developer |  |  |  | Sign-off date: | Review not started
Criteria per Development Phase |  | Status | Comments |  |  | Evaluator
Product Test Exit/User Acceptance Test Application Entry
Actual results
Problems remaining to be resolved
Resolved problems
Test Team Sign Off
Ensure actual results match expected results.
Ensure all conditions are successfully tested.
A clean execution pass has been achieved for all test scenarios.
Ensure the application product test manager has reviewed the application product test packet following the test.
Update test cycles and test conditions with testing status.
Make all test scripts available for the regression suite.
Update status of product.
Update checklist cross-references.
Collect appropriate metrics.
Obtain final sign-off by test management.
Ensure product performs all aspects of function as defined.
Determine whether one can gain a basic understanding of the product from the documentation.