## Cover Sheet
Pilot 2
New Codington Festival Online Project/FERS (Release 1)
Requirements Traceability Matrix
Version: <1.0>
Document Purpose: This document is a combined requirements gathering document and Requirements Traceability Matrix (RTM). It is used to document high level requirements, detailed product requirements and full traceability of these requirements through the software lifecycle. This template is part of the High Definition Lifecycle. This document is a living document and should be maintained for the duration of the project. The requirements traceability section of this document can be replaced by use of the Requisite Pro tool in the Accenture Delivery Suite. If ADT is used, then the requirements can be exported using the macros in the RTM sample available in ADM. Since a tool is not being used to trace requirements for this project, the RTM-Lifecycle Tracking tab is used to document requirement traceability across the full project lifecycle. Note that complete tracking is not available as this is beyond the scope of this course. Where necessary, some examples and instructions are also available.

## High-level Requirements
High-level Requirements
Project Name: | New Codington Project Online / FERS
Project Stage: | Plan
High-level Requirement ID | Business Topic | Requirement Name | Short Description | Priority | Release Number | Description | Requirement Source | Business/ Process Area | Stability | Dependencies | Status | Owner | Change Request ID | Is this an Interface Requirement? (Y/N) | Notes
Requirements and Traceability | Application Functionality | Visitor Registration | Allow users to register with an visitor account | High | 1 | FERS must allow users to register as visitors onto to the site | SOW | Public Relations | High | None | Approved | Michael Stevens | N/A | N | None
BREQ 2.0.0 | Application Functionality | Visitor Login | Allow visitors to login to site | High | 1 | FERS will provide login functionality for visitors to the site | SOW | Public Relations | High | BREQ 1.0.0 | Approved | Michael Stevens | N/A | N | None
BREQ 3.0.0 | Application Functionality | Update Visitor Account Details | Provide functionality to update account information | High | 1 | FERS will provide functionality to allow users to update account information. | SOW | Public Relations | High | BREQ 2.0.0 | Approved | Michael Stevens | N/A | N | None
BREQ 4.0.0 | Application Functionality | Event Ticket Registration | Allow visitors to register for an event | High | 1 | FERS must allow a visitor with a valid visitor account, to register for an event | SOW | Public Relations | High | BREQ 2.0.0 | Approved | Michael Stevens | N/A | N | None
BREQ 5.0.0 | Application Functionality | Event Ticket Release | Allow visitors to release a ticket for an event | High | 1 | FERS must allow a visitor with a valid visitor account, to release a ticket for an event | SOW | Public Relations | High | BREQ 4.0.0 | Approved | Michael Stevens | N/A | N | None
END OF FERS RELEASE 1 HIGH LEVEL REQUIREMENTS
Please don't Change below this line
Status
Approved
Rejected
Deferred
In-Progress
Note on E6: This column is linked with the Priority column on RTM - Lifecycle Tracking worksheet. The RTM - Lifecycle Tracking worksheet will pre-populate with the Priority column when it is entered here. High - Critical, can't live without Medium - Important-not critical but strongly desired by stakeholders Low - Optional, nice to have
Note on J6: The stability of the requirement (i.e. how likely it is for the requirement to change. High stability = low likelihood of change.)
Note on K6: Requirement IDs of all the requirements (both functional and non-functional) on which this requirement has a dependency.

## Product Requirements
Product Requirements
Project Name: | New Codington Project Online / FERS
Project Stage: | Analyse
Requirement ID | Business Topic | Requirement Name | Short Description | Requirement Type | Requirement Sub Type | Priority | Release Number | Long Description | Requirement Source | Business/ Process Area | Stability | Dependencies | Status | Owner | Change Request ID | Notes
BREQ 1.1.0 | Application Functionality | Visitor Account Setup | Provide functionality to allow users to set up account | Application | Functional | High | 1 | FERS will provide registration functionality to allow users to set up account to access the site | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.1.1 | Application Functionality | Enter required registration information | Users must enter aminimal amount of information to register | Application | Functional | High | 1 | FERS must require users to enter a minimal amount of personal information to register as visitors including: first name, last name, email address, address, phone number, password, and confirm password | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.1.2 | Application Functionality | Enter optional registration information | Optional information like home address can be entered | Application | Functional | High | 1 | FERS must allow users, when registering as visitors, to optionally provide (beyond the required personal information) their mailing address | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.2.0 | Application Functionality | Cancel Registration | Cancel registration during the registration process | Application | Functional | High | 1 | FERS must provide the capability for users to cancel registration during the registration process at any point before submitting the request to register | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.2.1 | Application Functionality | Cancel by navigating from the page | FERS must allow users to cancel registration by navigating from the page | Application | Functional | High | 1 | FERS must allow users to cancel registration by navigating from the page | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.2.2 | Application Functionality | Cancel function | A specific feature is to be provided to cancel registration | Application | Functional | High | 1 | FERS must allow users a specific function to cancel in the middle of the visitor account registration process | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.2.3 | Application Functionality | Lose unsaved changes on cancel | When cancelling during registration all entered data is lost | Application | Security and Control | High | 1 | FERS must remove and lose any updates performed when cancelling during the registration process | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.0 | Application Functionality | Validate Visitor Account Details | Validate personal information provided during the registration process | Application | Functional | High | 1 | FERS must provide validation to ensure users enter valid personal information during the registration process | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 1.3.1 | Application Functionality | Confirm Password entered on registration | It's required to enter a confirmation password during registration | Application | Functional | High | 1 | FERS must require a user to enter their password a second time to confirm their entered password for a visitor account | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 1.3.2 | Application Functionality | Phone Number needed for registration | It's required to enter a phone number during registration | Application | Functional | High | 1 | FERS must require a phone number for all visitor accounts | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.3 | Application Functionality | Phone Number format is digits only for registration | The phone entered during registration must only be digits | Application | Functional | High | 1 | FERS must require only digits to be entered for the phone number for all visitor accounts | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.4 | Application Functionality | Email address needed for registration | It's required to enter an email address during registration | Application | Functional | High | 1 | FERS must require an email address to be entered for all visitor accounts | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.5 | Application Functionality | Well formed email address needed for registration | The email address entered during registration must be well formed | Application | Functional | High | 1 | FERS must require a well formed email address to be entered for all visitor accounts | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.6 | Application Functionality | User Name required for registration | It's required to enter a user name during registration | Application | Functional | High | 1 | FERS must require a user name to be provided for all visitor accounts | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.7 | Application Functionality | Unique User Name required for registration | The user name entered during registration must not be in use by another visitor account | Application | Functional | High | 1 | FERS must require that a provided username has not already been used by another visitor account. | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.8 | Application Functionality | First Name required for registration | It's required to enter a first name during registration | Application | Functional | High | 1 | FERS must require a first name to be provided for all visitor accounts | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.9 | Application Functionality | Last Name required for registration | It's required to enter a last name during registration | Application | Functional | High | 1 | FERS must require a last name to be provided for all visitor accounts | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 1.3.10 | Application Functionality | Password required for registration | It's required to enter a password during registration | Application | Functional | High | 1 | FERS must require a password for all visitor accounts | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | None | Approved | NCCC | N/A | None
BREQ 2.0.1 | Application Functionality | Login required | To access the site a visitor must login with a user name and password | Application | Security and Control | High | 1 | FERS must require a visitor to login with their user name and password to access the site | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 2.0.2 | Application Functionality | Deny access | Access must be denied to a user if an invalid username and password is entered | Application | Security and Control | High | 1 | FERS must deny access to a visitor that uses an invalid user name and password combination | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.0 | Application Functionality | Update Vistor Information | Allow visitor to update personal information in visitor account | Application | Content | High | 1 | FERS must allow a visitor to update the personal information stored in their visitor account | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.1 | Application Functionality | Update First Name | A visitor can update their first name on their account | Application | Functional | High | 1 | FERS must allow a visitor to update the first name stored in their visitor account | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.2 | Application Functionality | Update Last Name | A visitor can update their last name on their account | Application | Functional | High | 1 | FERS must allow a visitor to update the last name stored in their visitor account | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.3 | Application Functionality | Update Password | A visitor can update their password on their account | Application | Functional | High | 1 | FERS must allow a visitor to update the password stored in their visitor account | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.4 | Application Functionality | Update Email Adress | A visitor can update their email address on their account | Application | Functional | High | 1 | FERS must allow a visitor to update the email address stored in their visitor account | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.5 | Application Functionality | Update Phone Number | A visitor can update their phone number on their account | Application | Functional | High | 1 | FERS must allow a visitor to update the phone # stored in their visitor account | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.6 | Application Functionality | Update Personal Address | A visitor can update their personal address on their account | Application | Functional | High | 1 | FERS must allow a visitor to update the personal address stored in their visitor account | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.1.7 | Application Functionality | Update User Name not allowed | A visitor can not update their user name on their account | Application | Functional | High | 1 | FERS must deny a visitor from updating their username stored in their visitor account | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.2.0 | Application Functionality | Cancel Account Update | Cancel without updating personal information on visitor account | Application | Functional | High | 1 | FERS must allow visitors to cancel without updating personal information on their visitor account | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.2.1 | Application Functionality | Cancel Update by Using Feature | A specific feature is to be provided to cancel update | Application | Functional | High | 1 | FERS must provide the capability for users to cancel updating personal information at any point before submitting the request to update | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.2.2 | Application Functionality | Cancel Update by Leaving Page | Cancel without updating personal information by going to another page | Application | Functional | High | 1 | FERS must allow users to cancel updating personal information by navigating from the page | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.0 | Application Functionality | Validate Visitor Account Update | Validate updated personal information on visitor account | Application | Functional | High | 1 | FERS must require validation to ensure users enter valid personal information when updating personal information on their visitor account | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.1 | Application Functionality | Validate First Name on Update | Validate that the first name was entered before update | Application | Functional | High | 1 | When updating a visitor account, FERS must validate that the first name is provided | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 3.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.2 | Application Functionality | Validate Last Name on Update | Validate that the last name was entered before update | Application | Functional | High | 1 | When updating a visitor account, FERS must validate that the last name is provided | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 4.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.3 | Application Functionality | Validate Email Address Exists on Update | Validate that the email address was entered before update | Application | Functional | High | 1 | When updating a visitor account, FERS must validate that an email address is provided | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 5.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.4 | Application Functionality | Validate Email Address is well formed on Update | Validate that the email address is well formed before update | Application | Functional | High | 1 | 4 - When updating a visitor account, FERS must validate that the email address provided is well formed | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.5 | Application Functionality | Validate Phone Number Exists on Update | Validate that the phone number was entered before update | Application | Functional | High | 1 | When updating a visitor account, FERS must validate that a phone number is provided | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.6 | Application Functionality | Validate Phone Number Is all digits on Update | Validate that the phone number contains only digits before update | Application | Functional | High | 1 | When updating a visitor account, FERS must validate that the phone number provided contains only digits | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.7 | Application Functionality | Validate Password Exists on Update | Validate that the password was entered before update | Application | Functional | High | 1 | When updating a visitor account, FERS must validate that a password is provided | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.8 | Application Functionality | Validate Confirm Password Exists on Update | Validate that the confirm password was entered before update | Application | Functional | High | 1 | When updating a visitor account, FERS must validate that a password is provided a second time to confirm the original password is entered as intended | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 3.3.9 | Application Functionality | Validate Password and Confirm Password on Update | Validate that the confirm password and password values are the same before update | Application | Functional | High | 1 | When updating a visitor account, FERS must validate that the password and confirm password provided are the same | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 4.0.1 | Application Functionality | Register for an Event | Allow visitor to register for an event with tickets available | Application | Functional | High | 1 | FERS must allow a visitor with a valid visitor account, to register for an event as long as at least one ticket remains | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 4.0.2 | Application Functionality | Deny registration for Sold Out Event | Deny visitor the ability to register for an event when no tickets available | Application | Functional | High | 1 | FERS must deny visitors with a valid visitor account, the ability to register for an event that has no tickets available | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 2.0.0 | Approved | NCCC | N/A | None
BREQ 5.0.1 | Application Functionality | Release Ticket for Registered Event | Allow visitor to give back or release tickets for an event previously registered for | Application | Functional | High | 1 | FERS must allow a visitor with a valid visitor account, to release a ticket for an event that was previously registered for | Meeting with NCCC Public Relations 24/5/10 | Public Relations | High | BREQ 4.0.0 | Approved | NCCC | N/A | None
END OF FERS RELEASE 1 PRODUCT REQUIREMENTS
Please Don't Change below the Line
Application
Deployment
Support
Technical
Training & Performance Spt
Sub-Types
Functional
Quality
Interface/Data
Security and Control
Content
Development Environment
Execution Environment
Operations Environment
Status
Proposed
Approved
Incorporated
Validated
Release
1
2
3
4
5
Priority
High
Medium
Low
Note on A7: This column is linked with the Requirements ID column on the RTM - Lifecycle Tracking worksheet. The RTM - Lifecycle Tracking sheet will pre-populate with the Requirement ID when it is entered here.
Note on D7: This column is linked with the Short Description column on RTM - Lifecycle Tracking worksheet. The RTM - Lifecycle Tracking worksheet will pre-populate with the Short Description column when it is entered here.
Note on F7: Only applicable for Application and Technical Requirements
Note on G7: This column is linked with the Priority column on RTM - Lifecycle Tracking worksheet. The RTM - Lifecycle Tracking worksheet will pre-populate with the Priority column when it is entered here. High - Critical, can't live without Medium - Important-not critical but strongly desired by stakeholders Low - Optional, nice to have
Note on H7: This column is linked with the Release Number column on RTM - Lifecycle Tracking worksheet. The RTM - Lifecycle Tracking sheet will pre-populate with the Release Number when it is entered here.
Note on L7: The stability of the requirement (i.e. how likely it is for the requirement to change. High stability = low likelihood of change.)
Note on M7: Requirement IDs of all the requirements (both functional and non-functional) on which this requirement has a dependency.

## RTM - Lifecycle Tracking
Requirements Traceability Matrix
NOTE: The Requirement ID, Short Description, Release Number and Priority columns are linked with the Requirements ID field on the Product Requirements worksheet. These field will pre-populate by the respective column on the Product Requirements worksheet.
Project Stage: | Analyse
Product Requirements |  |  |  |  | Analyze Stage | [8 empty] | Design Stage | [14 empty] | Build Stage
[5 empty] | Application |  |  |  | Technical Architecture |  |  |  |  | Application | [6 empty] | Technical Architecture |  |  |  |  | Test |  |  | Application |  |  |  | Test
Requirement ID | Short Description | Release Number | Priority (H, M, L) | High-level Requirement ID or SOW Reference | Use Case Diagram and User Scenarios | Use Case | Report and Batch Process Descriptions | System Integration Flow | Application Architecture Specification | Development Architecture Specification | Execution Architecture Specification | Operations Architecture Specification | Infrastructure Architecture Specification | System Integration Design | Component/ Class Design (CCD) | Report Design | Page Specification | Database Conversion Design | Physical Database Design | Assembly Test Conditions and Scenarios | Application Architecture Component Design | Development Architecture Component Design | Execution Architecture Component Design | Operations Architecture Component Design | Infrastructure Architecture Design | Application Product Test Conditions and Scenarios | Integration Product Test Conditions and Scenarios | Performance Test Conditions and Scenarios | Source Code Modules | Unit Test Conditions and Scenarios | Assembly Test Script | Unit Test Script | Application Product Test Script | Integration Product Test Script | Performance Test Script
BREQ 1.1.0 | Provide functionality to allow users to set up account | 1 | High | None | FERS_SC_1 | registerNewVisitor | Not Available | Not Available | Optional Reference available (Draft version) | Refer to the Development Architecture Specification Presentation for details | Not Available | Not Available | Refer to the Infrastructure Architecture Specification Presentation for details | Not Available | Refer to the CCD documents available with references to the Javadocs | Not Available | Not Available. Refer to the Wireframes for details. | Not Available | Refer to the Physical Database Document | Refer to the Test documents | Out -of scope for this project release | Out -of scope for this project release | Out -of scope for this project release | Out -of scope for this project release | Out -of scope for this project release | Refer to the Test documents | Out -of scope for this project release | Out -of scope for this project release | Refer to the Actual code | Refer to Unit Test conditions and Scenarios document Note that the traceability back to requirements wont be available completely in the above mentioned reference | Refer to Test documents & relevant test cycle control sheet for details | Refer to Test documents & relevant test cycle control sheet for details | Refer to the Test documents | Out -of scope for this project release | Out -of scope for this project release
BREQ 1.1.1 | Users must enter aminimal amount of information to register | 1 | High | None | FERS_SC_1 | registerNewVisitor
BREQ 1.1.2 | Optional information like home address can be entered | 1 | High | None | FERS_SC_1 | registerNewVisitor
BREQ 1.2.0 | Cancel registration during the registration process | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.2.1 | FERS must allow users to cancel registration by navigating from the page | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.2.2 | A specific feature is to be provided to cancel registration | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.2.3 | When cancelling during registration all entered data is lost | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.3.0 | Validate personal information provided during the registration process | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.3.1 | It's required to enter a confirmation password during registration | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.3.2 | It's required to enter a phone number during registration | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.3.3 | The phone entered during registration must only be digits | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.3.4 | It's required to enter an email address during registration | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.3.5 | The email address entered during registration must be well formed | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.3.6 | It's required to enter a user name during registration | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.3.7 | The user name entered during registration must not be in use by another visitor account | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.3.8 | It's required to enter a first name during registration | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.3.9 | It's required to enter a last name during registration | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 1.3.10 | It's required to enter a password during registration | 1 | High | Requirements and Traceability | FERS_SC_1 | registerNewVisitor
BREQ 2.0.1 | To access the site a visitor must login with a user name and password | 1 | High | BREQ 2.0.0 | FERS_SC_2,3,4 | loginVisitor
BREQ 2.0.2 | Access must be denied to a user if an invalid username and password is entered | 1 | High | BREQ 2.0.0 | FERS_SC_2,3,4 | loginVisitor
BREQ 3.1.0 | Allow visitor to update personal information in visitor account | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.1.1 | A visitor can update their first name on their account | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.1.2 | A visitor can update their last name on their account | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.1.3 | A visitor can update their password on their account | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.1.4 | A visitor can update their email address on their account | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.1.5 | A visitor can update their phone number on their account | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.1.6 | A visitor can update their personal address on their account | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.1.7 | A visitor can not update their user name on their account | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.2.0 | Cancel without updating personal information on visitor account | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.2.1 | A specific feature is to be provided to cancel update | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.2.2 | Cancel without updating personal information by going to another page | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.3.0 | Validate updated personal information on visitor account | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.3.1 | Validate that the first name was entered before update | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.3.2 | Validate that the last name was entered before update | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.3.3 | Validate that the email address was entered before update | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.3.4 | Validate that the email address is well formed before update | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.3.5 | Validate that the phone number was entered before update | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.3.6 | Validate that the phone number contains only digits before update | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.3.7 | Validate that the password was entered before update | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.3.8 | Validate that the confirm password was entered before update | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 3.3.9 | Validate that the confirm password and password values are the same before update | 1 | High | BREQ 3.0.0 | FERS_SC_4 | updateVisitorInfo
BREQ 4.0.1 | Allow visitor to register for an event with tickets available | 1 | High | BREQ 4.0.0 | FERS_SC_2 | registerForNewEvent
BREQ 4.0.2 | Deny visitor the ability to register for an event when no tickets available | 1 | High | BREQ 4.0.0 | FERS_SC_2 | registerForNewEvent
BREQ 5.0.1 | Allow visitor to give back or release tickets for an event previously registered for | 1 | High | BREQ 5.0.0 | FERS_SC_3 | unregisterFromExistingEvent
Note on A7: This column is linked with the Requirements ID field on the Product Requirements worksheet. This field will be pre-populated by the Requirements ID column on the Product Requirements worksheet. There is no need to enter the Requirements ID twice.
Note on B7: This column is linked to Short Description column on Product Requirements worksheet. This field will be pre-populated by the Short Description column on the Product Requirements worksheet. There is no need to enter the Short Description twice.
Note on C7: This column is linked to Release Number column on Product Requirements worksheet. This field will be pre-populated by the Release Number column on the Product Requirements worksheet. There is no need to enter the Release Number twice.
Note on D7: This column is linked to Priority column on Product Requirements worksheet. This field will be pre-populated by the Priority column on the Product Requirements worksheet. There is no need to enter the Priority twice.
Note on E7: Enter the ID of the corresponding high-level requirement. If such a high-level requirement does not exist, put in the reference to the Statement of Work.
Note on AG7: Note: For 'Unit Test' the script will be written in code implementing the test conditions for the scenario being coded, as opposed to the standard test script template.

## Assumptions
Assumptions
Project Stage: | Analyse
Assumption ID | Assumption | Stage | Status | Requirement ID | Date
ASID_001 | The FERS system will only store the data once the system has validated the customer account details | Plan | Valid | PR_002.10 | 2012-02-27
ASID_002 | The FERS System will not allow the customer to add any additonal contact details. | Plan | Valid | PR_0002.4 | 2012-02-27
ASID_003 | The FERS System does not have any email confirmation after visitor registers for an event or unregisters from an event or updates his/her information | Plan | Valid | None | 2012-03-12
ASID_004 | The FERS System does not have print friendly formatting on the website | Plan | Valid | None | 2012-03-12
ASID_003 | The FERS System does not have 'will-calls' on website for tickets to be collected at the ticket counter after purchasing online | Plan | Valid | None | 2012-03-12
ASID_003 | Register Link on myPortal page causes the “purchase”. Tickets are free. | Plan | Valid | None | 2012-03-12
Please do not change below this line
Stage
Plan
Analyse
Design
Build
Test
Deploy
Note on C4: Enter the stage of the project when the assumption was made.
Note on D4: Indicate in this cell if the assumption is still valid or if it has been invalidated by a new requirement.
Note on E4: When an assumption has been invalidated by a new requirement, track the requirement ID(s) in this column.
Note on F4: Insert the date the assumption was made, and update if it is invalidated.