## Cover Sheet
New Codington Festival Online Project / FERS (Release 1)
Test Cycle Control Sheet Template - Unit Test <TEAM NAME>
Version: <0.1>
This document is used to plan the test script execution for the New Codington Festival Online project. It has been used to define each unit test cycle and capture the test scripts which will be executed within each unit test cycle. This sheet will also be used to track testing execution progress. Since the unit tests are run in isolation, the order of the test script execution is not as important as in the other test stages where the Java class modules are integrated together (e.g. Assembly, Product, Performance, UAT, etc.). The scripts and cycles are listed by function of FERS to ensure all scenarios are covered. Also since unit tests should cover business cases, and not focus on implementation details, other developers should be able to read these unit tests to understand the business functionality of the code being tested.

## TCCS
Enter the start date in cell G7 to populate the plan.
[5 empty] | 2010-06-27 | [6 empty] | 2010-07-04 | [6 empty] | 2010-07-11 | [6 empty] | 2010-07-18 | [6 empty] | 2010-07-25 | [6 empty] | 2010-08-01 | [6 empty] | 2010-08-08 | [6 empty] | 2010-08-15 | [6 empty] | 2010-08-22
Cycle Profile Details |  |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Execution |  |  |  | Pass 1 |  | Pass 2 |  | Pass 3
Test Cycle ID | Scenario ID | Test Cycle Description | Test Script ID | Test Script | [63 empty] | Tester | Pass 1 | Pass 2 | Pass 3 | Started | Ended | Started | Ended | Started | Ended | Tester | time axis 2010-06-27 to 2010-08-28
 | time axis 2010-06-27 to 2010-08-28
1 |  | Normal Tests (Positive Outcomes) | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-06-29 to 2010-06-30
1.1 |  | Register New Visitor - Positive | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-06-29
| FERS.UT.AP491.TS.001.01 | Attempt to create a new visitor (all parameters are populated in Request Object) | FERS.UT.AP491.S.001 | FERS.UT.AP491.S.001_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.001.02 | Attempt to create a new visitor (all NOT NULL parameters are populated, some NULL parameters are NOT populated) | FERS.UT.AP491.S.001 | FERS.UT.AP491.S.001_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.028.01 | Insert New Visitor information into Database (username not already used in system) | FERS.UT.AP491.S.001 | FERS.UT.AP491.S.001_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.052.01 | Attempt to create a new visitor (visitor account created) | FERS.UT.AP491.S.001 | FERS.UT.AP491.S.001_UT.java | [64 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
1.2 |  | Visitor Login - Normal - Positive | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-06-29
| FERS.UT.AP491.TS.016.01 | No available events for the visitor(request and response object passed) | FERS.UT.AP491.S.002 | FERS.UT.AP491.S.002_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.016.02 | One available events for the visitor(request and response object passed) | FERS.UT.AP491.S.002 | FERS.UT.AP491.S.002_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.016.03 | More than one available events for the visitor(request and response object passed) | FERS.UT.AP491.S.002 | FERS.UT.AP491.S.002_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.018.01 | Successfully retrieve no events | FERS.UT.AP491.S.002 | FERS.UT.AP491.S.002_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.018.02 | Successfully retrieve one event | FERS.UT.AP491.S.002 | FERS.UT.AP491.S.002_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.018.03 | Successfully retrieve more than one event | FERS.UT.AP491.S.002 | FERS.UT.AP491.S.002_UT.java | [64 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
1.3 |  | Update Visitor Information - Positive | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-06-30
| FERS.UT.AP491.TS.064.01 | Attempt to Update Visitor Information (Visitor exists in system) | FERS.UT.AP491.S.003 | FERS.UT.AP491.S.003_UT.java | [64 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
1.4 |  | Register for Event - Positive | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-06-30
[69 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
1.5 |  | Unregister for Event - Positive | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-06-30
1.6 |  | Create an Exception - Positive | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-06-30
[69 empty] | Not Started | Not Started | Not Started
1.7 |  | Create a Connection - Positive | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-06-30
| FERS.UT.AP491.TS.072.01 | Attempt to create a connection(all parameters are correct) | FERS.UT.AP491.S.006 | FERS.UT.AP491.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
1.8 |  | Close Connection - Positive | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-06-30
| FERS.UT.AP491.TS.074.01 | Attempt to close a connection (all objects are valid) | FERS.UT.AP491.S.006 | FERS.UT.AP491.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
2 |  | Error Tests (Negative Outcomes) | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-01
2.1 |  | Register New Visitor - Negative | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-01
| FERS.UT.AP491.TS.002.01 | Attempt to create a new visitor (visitor already exists in system) | FERS.UT.AP491.S.007 | FERS.UT.AP491.S.007_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.029.01 | Insert New Visitor information into Database (username already in use in system) | FERS.UT.AP491.S.007 | FERS.UT.AP491.S.007_UT.java | [64 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
2.2 |  | Visitor Login - Negative | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-01
[69 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
2.3 |  | Update Visitor Information - Negative | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-01
[69 empty] | Not Started | Not Started | Not Started
2.4 |  | Register for Event - Negative | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-01
[69 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
2.5 |  | Unregister for Event - Negative | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-01
| FERS.UT.AP491.TS.014.01 | Attempt to unregister visitor from an event (valid visitor and event, not registered for event) | FERS.UT.AP491.S.011 | FERS.UT.AP491.S.011_UT.java | [64 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
2.6 |  | Create an Exception - Negative | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-01
| FERS.UT.AP491.TS.070.01 | Attempt to throw an Exception (NULL message and throwable object) | FERS.UT.AP491.S.012 | FERS.UT.AP491.S.012_UT.java | [64 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
3 |  | Exception Tests (Outcomes that throw Exceptions) | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-01 to 2010-07-02
3.1 |  | Register New Visitor - Exception | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-01
| FERS.UT.AP491.TS.003.01 | Attempt to create a new visitor (missing Request object) | FERS.UT.AP491.S.013 | FERS.UT.AP491.S.013_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.003.02 | Attempt to create a new visitor (missing Reponse object) | FERS.UT.AP491.S.013 | FERS.UT.AP491.S.013_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.003.03 | Attempt to create a new visitor (missing objects) | FERS.UT.AP491.S.013 | FERS.UT.AP491.S.013_UT.java | [64 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
3.2 |  | Visitor Login - Exception | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-01
| FERS.UT.AP491.TS.017.01 | See all available events for the visitor(null request object) | FERS.UT.AP491.S.014 | FERS.UT.AP491.S.014_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.017.02 | See all available events for the visitor(null response object) | FERS.UT.AP491.S.014 | FERS.UT.AP491.S.014_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.017.03 | See all available events for the visitor(both objects are null ) | FERS.UT.AP491.S.014 | FERS.UT.AP491.S.014_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.019.01 | Attempt to connection to database (invalid JDBC Driver) | FERS.UT.AP491.S.014 | FERS.UT.AP491.S.014_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.019.02 | Attempt to connection to database (invalid URL) | FERS.UT.AP491.S.014 | FERS.UT.AP491.S.014_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.046.01 | Attempt to retrieve information on all upcoming events (ClassNotFoundException exception occurs) | FERS.UT.AP491.S.014 | FERS.UT.AP491.S.014_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.UT.AP491.TS.046.02 | Attempt to retrieve information on all upcoming events (SQLException exception occurs) | FERS.UT.AP491.S.014 | FERS.UT.AP491.S.014_UT.java | [64 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
3.3 |  | Update Visitor Information - Exception | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-02
[69 empty] | Not Started | Not Started | Not Started
3.4 |  | Register for Event - Exception | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-02
[69 empty] | Not Started | Not Started | Not Started
3.5 |  | Unregister for Event - Exception | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-02
[69 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
[69 empty] | Not Started | Not Started | Not Started
3.6 |  | Create an Exception - Exception | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-02
[69 empty] | Not Started | Not Started | Not Started
3.7 |  | Create a Connection - Exception | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-02
[69 empty] | Not Started | Not Started | Not Started
3.8 |  | Close a Connection - Exception | [66 empty] | Not Started | Not Started | Not Started | bar: 2010-07-02
[69 empty] | Not Started | Not Started | Not Started
END OF TEST CYCLE CONTROL SHEET