## Cover Sheet
New Codington Festival Online Project / FERS (Release 2)
Defect List - <Team Name>
Version: <3.6>
This document is used to log and track the status of defects (previously called System Investigation Requests). A defect is defined as a gap between the actual and expected results. The expected results are based on expectations that are set by client requirements. The documentation of defects during testing provides a place to identify downstream impacts of the defect on other teams. Also included in the documentation are the steps taken to resolve the defect and any testing requirements required to consider the defect corrected. Place your team name in the area marked <Team Name> above.

## FERS R2 Defects
Defect ID | Module | Defect Type | Defect Description | Potential Resolution | Status | Priority | Created by | Created Date | Assigned To | Comments | Resolved Date | Resolution Description | STATUS: | Issue Type: | Issue Priority | Description
FERS.R2.SIR.001 | registration.jsp | Design Change | Limit the size of the text fields to the database field length for all text boxes |  | 01 - Open | 02 - MEDIUM | Jada Jenkins | 2010-07-11 |  |  |  |  | 01 - Open | Comments | 01 - HIGH | Flawed functionality
FERS.R2.SIR.002 | registration.jsp | Validation | Add validation that the only a limited number of special characters can be entered in the text fields. | The only special characters allowed are @, . , -, (, ), #, _ | 01 - Open | 03 - LOW | Jada Jenkins | 2010-07-11 |  |  |  |  | 02 - Open: Retest Failed | Design Change | 02 - MEDIUM | Cosmetic Issue - Needs to be fixed but not a rush
FERS.R2.SIR.003 | visitormain.jsp | Syntax | Change seats to tickets | Should consider going with tickets instead of seats. Not all attractions with have "seats" | 01 - Open | 03 - LOW | Jada Jenkins | 2010-07-11 |  |  |  |  | 05- Validation In-Progress | Logic | 03 - LOW | Nice to have fix
FERS.R2.SIR.004 | catalog.htm | Syntax | Change table title text | Can you change the text to say "Upcoming Events" | 01 - Open | 02 - MEDIUM | Rishi Srinivasan | 2010-07-11 |  |  |  |  | 10 - Under Review | Syntax | 99 - INFORMATION
FERS.R2.SIR.005 | catalog.htm | Syntax | Change message when "no seats left" | Make the message "SOLD OUT" | 01 - Open | 02 - MEDIUM | Rishi Srinivasan | 2010-07-11 |  |  |  |  | 20 - Fix In Progress
FERS.R2.SIR.006 | searchVisitor.htm | Syntax | Change message when "no seats left" | Make the message "SOLD OUT" in the Upcoming Events table | 01 - Open | 02 - MEDIUM | Rishi Srinivasan | 2010-07-11 |  |  |  |  | 30 - Fix Complete: DEV Testing | Validation
FERS.R2.SIR.007 | updatevisitor.jsp | Logic | Festival Registration System link gives a 404 HTTP failure | Consider removing the link and make it static text. | 01 - Open | 01 - HIGH | Armand Navabi | 2010-07-12 |  |  |  |  | 40 - Ready for Retest | Other
FERS.R2.SIR.008 | updatevisitor.jsp | Validation | Add validation that the only a limited number of special characters can be entered in the text fields. | The only special characters allowed are @, . , -, (, ), #, _ | 01 - Open | 03 - LOW | Armand Navabi | 2010-07-12 |  |  |  |  | 50 - Fix Complete
FERS.R2.SIR.009 | updatevisitor.jsp | Logic | About link gives a 404 HTTP failure | Should go to the about.jsp | 01 - Open | 01 - HIGH | Len Sharples | 2010-07-12 |  |  |  |  | 60 - Closed
FERS.R2.SIR.010 | visitormain.jsp | Logic | Display a message when no events are upcoming (no events in the events table) | In the table can we put in the row under the columns the following message: "There are currently no events upcoming. Please check back later. Thanks for visiting the event portal!". If the logic is too challenging to get to work, it can be under the table. | 01 - Open | 02 - MEDIUM | Evan Ward | 2010-07-12 |  |  |  |  | 94 - On Hold
FERS.R2.SIR.011 | catalog.htm | Logic | Display a message when no events are upcoming (no events in the events table) | In the table can we put in the row under the columns the following message: "There are currently no events upcoming. Please check back later. Thanks for visiting the event portal!". If the logic is too challenging to get to work, it can be under the table. | 01 - Open | 02 - MEDIUM | Evan Ward | 2010-07-12 |  |  |  |  | 95 - Defer to Release 2 - Participants complete
FERS.R2.SIR.012 | visitormain.jsp | Syntax | Update all column heading that are not in "Title Case" like Event id should be Event ID, description should be Description, Event type should be Event Type. |  | 01 - Open | 02 - MEDIUM | Armand Navabi | 2010-07-12 |  |  |  |  | 96 - Defer to "Release 3" - Storyline
FERS.R2.SIR.013 | about.jsp | Logic | Festival Registration System link gives a 404 HTTP failure | Consider removing the link and make it static text. | 01 - Open | 01 - HIGH | Armand Navabi | 2010-07-12 |  |  |  |  | 97 - Rejected: Duplicate
FERS.R2.SIR.014 | catalog.htm | Syntax | Update all column heading that are not in "Title Case" like Event id should be Event ID, Event name should be Event Name and Event type should be Event Type. |  | 01 - Open | 02 - MEDIUM | Rishi Srinivasan | 2010-07-12 |  |  |  |  | 98 - Rejected: Out of Scope
FERS.R2.SIR.015 | about.jsp | Syntax | Update the Content displayed on the about page. | Please correct the grammar in the text. 2nd sentence: Change "FERS allows ease of use to view and registration to various events..." to "FERS allows visitors to easily view and register for various events..." 3rd sentence: Change "FERS was created in a joint with Accenture, Ltd and the New Codington Chamber of Commerce." to "FERS is the result of a joint venture between Accenture, Ltd and the New Codington Chamber of Commerce." 5th sentence: Change "... events or activities that are schedule via..." to "... events or activities that are scheduled ..." 6th sentence: Change "Please frequently check the site for latest events are ticket availability." to "Please frequently check this site for the latest event status and ticket availability." | 01 - Open | 02 - MEDIUM | Armand Navabi | 2010-07-13 |  |  |  |  | 99 - Request for more information
FERS.R2.SIR.016 | visitormain.jsp | Syntax | Update the content displayed in the Personal Information section of the Portal Page. | The UserName and Visitor ID can't be changed by the user so it should not be displayed. So instead display the First Name (first row) and Last Name (second row) | 01 - Open | 02 - MEDIUM | Len Sharples | 2010-07-13
FERS.R2.SIR.017 | visitormain.jsp | Syntax | Update the content formatting in the Personal Information section of the Portal Page. | In the Personal information section make sure that the Label is formatted with bold text and the colon (':') immediately following the label text with two spaces of text afterwards. Then the value is displayed (but the text is NOT bolded) | 01 - Open | 02 - MEDIUM | Rishi Srinivasan | 2010-07-13
FERS.R2.SIR.018 | visitormain.jsp | Logic | Address field is not a required field, but some content should be displayed | When no address is provided in the visitor's personal information, default to show the phrase "<no address provided>" | 01 - Open | 02 - MEDIUM | Rishi Srinivasan | 2010-07-13
FERS.R2.SIR.019 | Various | Syntax | Remove references to 'user' and change to ‘visitor’ | Any screens that have the word ‘user’ displayed, should be changed to say ‘visitor’. | 01 - Open | 03 - LOW | Len Sharples | 2010-07-13
FERS.R2.SIR.020 | Various | Syntax | Need to improve some validation messages | Please make the validation error messages more descriptive. | 01 - Open | 03 - LOW | Evan Ward | 2010-07-13
FERS.R2.SIR.021 | about.jsp | Syntax | Please change client name | Please change 'New Codington Chamber of Commerce' to 'New Codington City Council' | 01 - Open | 01 - HIGH | Evan Ward | 2010-07-13
Last Row | Last Row | Comments | Last Row | Last Row | Last Row | 01 - HIGH | Last Row | Last Row | Last Row | Last Row | Last Row | Last Row
Note on A1: Unique ID for Issues Format: FERS_<Codebase>_00n <Codebase> Values PRE= Pre-Change Request Solution PART = Participant Code POST = Post-Change Request Solution
Note on B1: Code module file name
Note on C1: Issue Type: Comments Design Change Logic Syntax Validation
Note on F1: STATUS: 01 - Open 02 - Open: Retest Failed 10 - Under Review 20 - Fix In Progress 30 - Fix Complete: DEV Testing 40 - Ready for Retest 50 - Fix Complete 60 - Closed 97 - Rejected: Duplicate 98 - Rejected: Out of Scope 99 - Request for more information
Note on G1: Issue Priority 01 - HIGH 02 - MEDIUM 03 - LOW
Note on K1: Developer Comments
Note on M1: Questions and comments entered here. Use the following format: [Initials YY/MM/DD] <Comment Description and details>