## Cover Sheet
New Codington Festival Online Project / FERS (Release 2)
Test Cycle Control Sheet Product Test
Version: <0.1>
This document is used to plan test script execution for the New Codington Festival Online project. It defines each product test cycle and captures the test scripts which will be executed within each product test cycle. The Team Lead will use this document to track the progress of testing. Because product tests are run on the full application, the order of the test script execution is important. The scripts and cycles are listed by use case to ensure all of the scenarios are covered. Also since product tests cover business cases, and not focus on implementation details, other developers should be able to read these product tests to understand the business functionality of the code being tested. Note: The test scenarios where the cell color is orange indicate Change Requests that were approved by the CCB (Change Control Board).

## TCCS - Cycle Per Use Case
Enter the start date in cell G7 to populate the plan.
[5 empty] | 2010-06-27 | [6 empty] | 2010-07-04 | [6 empty] | 2010-07-11 | [6 empty] | 2010-07-18 | [6 empty] | 2010-07-25 | [6 empty] | 2010-08-01 | [6 empty] | 2010-08-08 | [6 empty] | 2010-08-15 | [6 empty] | 2010-08-22
Cycle Profile Details |  |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Execution |  |  |  | Pass 1 |  | Pass 2 |  | Pass 3
Test Cycle ID | Scenario ID | Test Cycle Description | Test Script ID | Test Script | 2010-06-27 | 2010-06-28 | 2010-06-29 | 2010-06-30 | 2010-07-01 | 2010-07-02 | 2010-07-03 | 2010-07-04 | 2010-07-05 | 2010-07-06 | 2010-07-07 | 2010-07-08 | 2010-07-09 | 2010-07-10 | 2010-07-11 | 2010-07-12 | 2010-07-13 | 2010-07-14 | 2010-07-15 | 2010-07-16 | 2010-07-17 | 2010-07-18 | 2010-07-19 | 2010-07-20 | 2010-07-21 | 2010-07-22 | 2010-07-23 | 2010-07-24 | 2010-07-25 | 2010-07-26 | 2010-07-27 | 2010-07-28 | 2010-07-29 | 2010-07-30 | 2010-07-31 | 2010-08-01 | 2010-08-02 | 2010-08-03 | 2010-08-04 | 2010-08-05 | 2010-08-06 | 2010-08-07 | 2010-08-08 | 2010-08-09 | 2010-08-10 | 2010-08-11 | 2010-08-12 | 2010-08-13 | 2010-08-14 | 2010-08-15 | 2010-08-16 | 2010-08-17 | 2010-08-18 | 2010-08-19 | 2010-08-20 | 2010-08-21 | 2010-08-22 | 2010-08-23 | 2010-08-24 | 2010-08-25 | 2010-08-26 | 2010-08-27 | 2010-08-28 | Tester | Pass 1 | Pass 2 | Pass 3 | Started | Ended | Started | Ended | Started | Ended | Tester
[5 empty] | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa
1 |  | Use Case 1 - Register New Visitor | [66 empty] | Not Started | Not Started | Not Started
1.1 |  | Register New Visitor - Successful Registration | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.001.01 | Register New Visitor (all fields populated) | FERS.APT.AP212.S.001 | FERS.APT.AP212.S.001_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.001.02 | Register New Visitor (all NOT-NULL fields populated only) | FERS.APT.AP212.S.001 | FERS.APT.AP212.S.001_APT.java | [64 empty] | Not Started | Not Started | Not Started
1.2 |  | Register New Visitor - Cancel Registration | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.002.01 | Navigate back to Login Page | FERS.APT.AP212.S.001 | FERS.APT.AP212.S.001_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.002.02 | Cancel Registration Option. | FERS.APT.AP212.S.001 | FERS.APT.AP212.S.001_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.002.03 | Return back to Registration page | FERS.APT.AP212.S.001 | FERS.APT.AP212.S.001_APT.java | [64 empty] | Not Started | Not Started | Not Started
1.3 |  | Register New Visitor - Field Values Fail Validation Rules | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.003.01 | Password/Confirm Password not the same | FERS.APT.AP212.S.002 | FERS.APT.AP212.S.002_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.003.02 | Phone number not all numbers | FERS.APT.AP212.S.002 | FERS.APT.AP212.S.002_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.003.03 | email ID not formed correctly | FERS.APT.AP212.S.002 | FERS.APT.AP212.S.002_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.003.04 | username already used by a different user | FERS.APT.AP212.S.002 | FERS.APT.AP212.S.002_APT.java | [64 empty] | Not Started | Not Started | Not Started
1.4 |  | Register New Visitor - Required Fields not Populated | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.004.01 | First Name not populated | FERS.APT.AP212.S.003 | FERS.APT.AP212.S.003_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.004.02 | Last Name not populated | FERS.APT.AP212.S.003 | FERS.APT.AP212.S.003_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.004.03 | User Name not populated | FERS.APT.AP212.S.003 | FERS.APT.AP212.S.003_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.004.04 | Phone number not populated | FERS.APT.AP212.S.003 | FERS.APT.AP212.S.003_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.004.05 | Email Address not populated | FERS.APT.AP212.S.003 | FERS.APT.AP212.S.003_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.004.06 | Password not populated | FERS.APT.AP212.S.003 | FERS.APT.AP212.S.003_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.004.07 | Confirm Password not populated | FERS.APT.AP212.S.003 | FERS.APT.AP212.S.003_APT.java | [64 empty] | Not Started | Not Started | Not Started
2 |  | Use Case 2 - Visitor Login | [66 empty] | Not Started | Not Started | Not Started
2.1 |  | Visitor Login - Successful Login | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.005.01 | Login Successfully | FERS.APT.AP212.S.004 | FERS.APT.AP212.S.004_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.005.02 | Logout , Login with same ID | FERS.APT.AP212.S.004 | FERS.APT.AP212.S.004_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.005.03 | Logout , Login with different ID | FERS.APT.AP212.S.004 | FERS.APT.AP212.S.004_APT.java | [64 empty] | Not Started | Not Started | Not Started
2.2 |  | Visitor Login - Username/Password combination invalid | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.006.01 | Valid Visitor Name, Invalid Password | FERS.APT.AP212.S.004 | FERS.APT.AP212.S.004_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.006.02 | Invalid Visitor Name, Valid Password | FERS.APT.AP212.S.004 | FERS.APT.AP212.S.004_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.006.03 | Blank Visitor Name | FERS.APT.AP212.S.004 | FERS.APT.AP212.S.004_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.006.04 | Blank Password | FERS.APT.AP212.S.004 | FERS.APT.AP212.S.004_APT.java | [64 empty] | Not Started | Not Started | Not Started
3 |  | Use Case 3 - Update Visitor Information | [66 empty] | Not Started | Not Started | Not Started
3.1 |  | Update Visitor Information - Successful Account Update | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.007.01 | Update Visitor First Name | FERS.APT.AP212.S.005 | FERS.APT.AP212.S.005_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.007.02 | Update Visitor Last Name | FERS.APT.AP212.S.005 | FERS.APT.AP212.S.005_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.007.03 | Update Visitor Password | FERS.APT.AP212.S.005 | FERS.APT.AP212.S.005_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.007.04 | Update Visitor Email | FERS.APT.AP212.S.005 | FERS.APT.AP212.S.005_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.007.05 | Update Visitor Phone No. | FERS.APT.AP212.S.005 | FERS.APT.AP212.S.005_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.007.06 | Update Visitor Address | FERS.APT.AP212.S.005 | FERS.APT.AP212.S.005_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.007.07 | Update User Name | FERS.APT.AP212.S.005 | FERS.APT.AP212.S.005_APT.java | [64 empty] | Not Started | Not Started | Not Started
3.2 |  | Update Visitor Information - Navigate to About Page | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.008.01 | Cancel with no change to visitor info | FERS.APT.AP212.S.006 | FERS.APT.AP212.S.006_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.008.02 | Cancel with changes to all values | FERS.APT.AP212.S.006 | FERS.APT.AP212.S.006_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.008.03 | Logout of application | FERS.APT.AP212.S.006 | FERS.APT.AP212.S.006_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.008.04 | Navigate to About Page | FERS.APT.AP212.S.006 | FERS.APT.AP212.S.006_APT.java | [64 empty] | Not Started | Not Started | Not Started
3.3 |  | Update Visitor Information - Required fields not populated | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.009.01 | Remove First Name value | FERS.APT.AP212.S.007 | FERS.APT.AP212.S.007_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.009.02 | Remove Last Name value | FERS.APT.AP212.S.007 | FERS.APT.AP212.S.007_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.009.03 | Remove Email | FERS.APT.AP212.S.007 | FERS.APT.AP212.S.007_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.009.04 | Remove Phone # | FERS.APT.AP212.S.007 | FERS.APT.AP212.S.007_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.009.05 | No Password entered, Confirm password entered | FERS.APT.AP212.S.007 | FERS.APT.AP212.S.007_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.009.06 | No Confirm Password entered, password entered | FERS.APT.AP212.S.007 | FERS.APT.AP212.S.007_APT.java | [64 empty] | Not Started | Not Started | Not Started
3.4 |  | Update Visitor Information - Field Values Fails Validation Rules | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.010.01 | Password/Confirm Password not the same | FERS.APT.AP212.S.007 | FERS.APT.AP212.S.007_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.010.02 | Phone number not all numbers | FERS.APT.AP212.S.007 | FERS.APT.AP212.S.007_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.010.03 | email ID not formed correctly | FERS.APT.AP212.S.007 | FERS.APT.AP212.S.007_APT.java | [64 empty] | Not Started | Not Started | Not Started
4 |  | Use Case 4 - Register for Event | [66 empty] | Not Started | Not Started | Not Started
4.1 |  | Register for Event Seesion - Positive | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.011.01 | Register for an event session (tickets available) | FERS.APT.AP212.S.008 | FERS.APT.AP212.S.008_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.011.02 | Register for an event session (one ticket available) | FERS.APT.AP212.S.008 | FERS.APT.AP212.S.008_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.011.03 | Register for an event session (tickets NOT available) | FERS.APT.AP212.S.008 | FERS.APT.AP212.S.008_APT.java | [64 empty] | Not Started | Not Started | Not Started
5 |  | Use Case 5 - Unregister from Event | [66 empty] | Not Started | Not Started | Not Started
5.1 |  | Unregister for Event Session - Positive | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.012.01 | Unregister from an event session | FERS.APT.AP212.S.008 | FERS.APT.AP212.S.008_APT.java | [64 empty] | Not Started | Not Started | Not Started
6 |  | Use Case 6: View Event Catalog | [66 empty] | Not Started | Not Started | Not Started
6.1 |  | Review the Event Catalog - Positive | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.013.01 | Navigate to the Event Catalog page (More than one upcoming event session is available) | FERS.APT.AP212.S.009 | FERS.APT.AP212.S.009_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.013.02 | Navigate to the Event Catalog page (One upcoming event session is available) | FERS.APT.AP212.S.010 | FERS.APT.AP212.S.010_APT.java | [64 empty] | Not Started | Not Started | Not Started
6.1 |  | Review the Event Catalog - Negative | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.013.03 | Navigate to the Event Catalog page (No upcoming event session is available in the system) | FERS.APT.AP212.S.011 | FERS.APT.AP212.S.011_APT.java | [64 empty] | Not Started | Not Started | Not Started
7 |  | Use Case 7: Search Event List | [66 empty] | Not Started | Not Started | Not Started
7.1 |  | Search Event List - Positive | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.014.01 | Search for an event with more than one event session returned on the Event Catalog Page | FERS.APT.AP212.S.012 | FERS.APT.AP212.S.012_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.014.02 | Search for an event with one event session returned on the Event Catalog Page | FERS.APT.AP212.S.012 | FERS.APT.AP212.S.012_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.014.03 | Remove filter (all upcoming events appear) on the Event Catalog Page | FERS.APT.AP212.S.012 | FERS.APT.AP212.S.012_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.015.01 | Search for an event with more than one event session returned on the Festival Portal Page | FERS.APT.AP212.S.012 | FERS.APT.AP212.S.012_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.015.02 | Search for an event with one event session returned on the Festival Portal Page | FERS.APT.AP212.S.012 | FERS.APT.AP212.S.012_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.015.03 | Remove filter (all upcoming events appear) on the Festival Portal Page | FERS.APT.AP212.S.012 | FERS.APT.AP212.S.012_APT.java | [64 empty] | Not Started | Not Started | Not Started
7.2 |  | Search Event List - Negative | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.014.04 | Search for an event with no event sessions returned on the Event Catalog Page | FERS.APT.AP212.S.012 | FERS.APT.AP212.S.012_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.014.05 | Put invalid characters in the search field on the Event Catalog Page | FERS.APT.AP212.S.012 | FERS.APT.AP212.S.012_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.015.04 | Search for an event with no event sessions returned on the Festival Portal Page | FERS.APT.AP212.S.012 | FERS.APT.AP212.S.012_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.015.05 | Put invalid characters in the search field on the Festival Portal Page | FERS.APT.AP212.S.012 | FERS.APT.AP212.S.012_APT.java | [64 empty] | Not Started | Not Started | Not Started
8 |  | Use Case 8: Sort Event List | [66 empty] | Not Started | Not Started | Not Started
8.1 |  | Sort Event List - Positive | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.016.01 | Sort in ascending order by Event Name on the Event Catalog page (More than one upcoming event session is available in the system) | FERS.APT.AP212.S.009 | FERS.APT.AP212.S.009_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.016.02 | Sort in descending order by Event Name on the Event Catalog page (More than one upcoming event session is available in the system) | FERS.APT.AP212.S.009 | FERS.APT.AP212.S.009_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.017.01 | Sort in ascending order by Event Name on the Festival Portal page (More than one upcoming event session is available in the system) | FERS.APT.AP212.S.009 | FERS.APT.AP212.S.009_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.017.02 | Sort in descending order by Event Name on the Festival Portal page (More than one upcoming event session is available in the system) | FERS.APT.AP212.S.009 | FERS.APT.AP212.S.009_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.016.03 | Sort in ascending order by Event Name on the Event Catalog page (One upcoming event session is available in the system) | FERS.APT.AP212.S.010 | FERS.APT.AP212.S.010_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.016.04 | Sort in descending order by Event Name on the Event Catalog page (One upcoming event session is available in the system) | FERS.APT.AP212.S.010 | FERS.APT.AP212.S.010_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.017.03 | Sort in ascending order by Event Name on the Festival Portal page (One upcoming event session is available in the system) | FERS.APT.AP212.S.010 | FERS.APT.AP212.S.010_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.017.04 | Sort in descending order by Event Name on the Festival Portal page (One upcoming event session is available in the system) | FERS.APT.AP212.S.010 | FERS.APT.AP212.S.010_APT.java | [64 empty] | Not Started | Not Started | Not Started
8.2 |  | Sort Event List - Negative | [66 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.016.05 | Sort in ascending order by Event Name on the Event Catalog page (No upcoming event session is available in the system) | FERS.APT.AP212.S.011 | FERS.APT.AP212.S.011_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.016.06 | Sort in descending order by Event Name on the Event Catalog page (No upcoming event session is available in the system) | FERS.APT.AP212.S.011 | FERS.APT.AP212.S.011_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.017.05 | Sort in ascending order by Event Name on the Festival Portal page (No upcoming event session is available in the system) | FERS.APT.AP212.S.011 | FERS.APT.AP212.S.011_APT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.APT.AP212.TS.017.06 | Sort in descending order by Event Name on the Festival Portal page (No upcoming event session is available in the system) | FERS.APT.AP212.S.011 | FERS.APT.AP212.S.011_APT.java | [64 empty] | Not Started | Not Started | Not Started
END OF TEST CYCLE CONTROL SHEET