## Cover Sheet
New Codington Festival Online Project / FERS (Release 2)
Test Cycle Control Sheet - Assembly Test
Version: <0.1>
This document is used to plan test script execution for the New Codington Festival Online project. It has been used to define each assembly test cycle and capture the test scripts which will be executed within each assembly test cycle. This sheet will also be used to track testing execution progress. Since the assembly tests are run by integrating components, the order of the test script execution is important as in the other test stages where the Java class modules are integrated together (e.g. Product, Performance, UAT, etc.). The scripts and cycles are listed by function to ensure all scenarios are covered. Also since assembly tests should cover business cases, and not focus on implementation details, other developers should be able to read these assembly tests to understand the business functionality of the code being tested. The 1-Vertical Test-TCCS tab shows the TCCS when only one assembly test is performed: Testing the integration of components from the Controller Classes to the Database and returning the results. Note: The test scenarios where the cell color is orange indicate Change Requests that were approved by the CCB.

## 1 Level-Vertical Test-TCCS
Enter the start date in cell G7 to populate the plan.
[5 empty] | 2010-06-27 | [6 empty] | 2010-07-04 | [6 empty] | 2010-07-11 | [6 empty] | 2010-07-18 | [6 empty] | 2010-07-25 | [6 empty] | 2010-08-01 | [6 empty] | 2010-08-08 | [6 empty] | 2010-08-15 | [6 empty] | 2010-08-22
Cycle Profile Details |  |  |  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Execution |  |  |  | Pass 1 |  | Pass 2 |  | Pass 3
Test Cycle ID | Scenario ID | Test Cycle Description | Test Script ID | Test Script | 2010-06-27 | 2010-06-28 | 2010-06-29 | 2010-06-30 | 2010-07-01 | 2010-07-02 | 2010-07-03 | 2010-07-04 | 2010-07-05 | 2010-07-06 | 2010-07-07 | 2010-07-08 | 2010-07-09 | 2010-07-10 | 2010-07-11 | 2010-07-12 | 2010-07-13 | 2010-07-14 | 2010-07-15 | 2010-07-16 | 2010-07-17 | 2010-07-18 | 2010-07-19 | 2010-07-20 | 2010-07-21 | 2010-07-22 | 2010-07-23 | 2010-07-24 | 2010-07-25 | 2010-07-26 | 2010-07-27 | 2010-07-28 | 2010-07-29 | 2010-07-30 | 2010-07-31 | 2010-08-01 | 2010-08-02 | 2010-08-03 | 2010-08-04 | 2010-08-05 | 2010-08-06 | 2010-08-07 | 2010-08-08 | 2010-08-09 | 2010-08-10 | 2010-08-11 | 2010-08-12 | 2010-08-13 | 2010-08-14 | 2010-08-15 | 2010-08-16 | 2010-08-17 | 2010-08-18 | 2010-08-19 | 2010-08-20 | 2010-08-21 | 2010-08-22 | 2010-08-23 | 2010-08-24 | 2010-08-25 | 2010-08-26 | 2010-08-27 | 2010-08-28 | Tester | Pass 1 | Pass 2 | Pass 3 | Started | Ended | Started | Ended | Started | Ended | Tester
[5 empty] | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa
1 |  | Normal Tests (Positive Outcomes) | [66 empty] | Not Started | Not Started | Not Started
1.01 |  | Register New Visitor - Positive | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.030.01 | Attempt to create a new visitor (all parameters are populated in Request Object) | FERS.AT.AP331.S.001 | FERS.AT.AP331.S.001_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.030.02 | Attempt to create a new visitor (all NOT NULL parameters are populated, some NULL parameters are NOT populated) | FERS.AT.AP331.S.001 | FERS.AT.AP331.S.001_UT.java | [64 empty] | Not Started | Not Started | Not Started
1.02 |  | Visitor Login - Normal - Positive | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.033.01 | Attempt to find visitor using login credentials (valid username and password) | FERS.AT.AP331.S.002 | FERS.AT.AP331.S.002_UT.java | [64 empty] | Not Started | Not Started | Not Started
1.03 |  | Update Visitor Information - Positive | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.039.01 | Attempt to update visitor information (all parameters are populated) | FERS.AT.AP331.S.003 | FERS.AT.AP331.S.003_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.039.02 | Attempt to update visitor information (all NOT NULL parameters are populated, some NULL parameters are NOT populated) | FERS.AT.AP331.S.003 | FERS.AT.AP331.S.003_UT.java | [64 empty] | Not Started | Not Started | Not Started
1.04 |  | Register for Event - Positive | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.036.01 | Attempt to register visitor for an event session (valid visitor and event session, not registered for event session) | FERS.AT.AP331.S.004 | FERS.AT.AP331.S.004_UT.java | [64 empty] | Not Started | Not Started | Not Started
1.05 |  | Unregister for Event - Positive | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.042.01 | Attempt to unregister visitor from an event session (valid visitor and event session, registered for event session) | FERS.AT.AP331.S.005 | FERS.AT.AP331.S.005_UT.java | [64 empty] | Not Started | Not Started | Not Started
1.06 |  | Show All Events - Positive | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.028.01 | No available events for the visitor(request and response object passed) | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.028.02 | One available events for the visitor(request and response object passed) | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.028.03 | More than one available events for the visitor(request and response object passed) | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
1.07 |  | searchEventsByNameCatalog (Positive) | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.044.01 | Attempt to search for an event session by name on the Event Catalog Page (valid visitor and event name) - multiple events returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.044.02 | Attempt to search for an event session by name on the Event Catalog Page (valid visitor and invalid eventname) - one event session returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.044.03 | Attempt to search for an event session by name on the Event Catalog Page (valid visitor and invalid eventname) - no event sessions returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
1.08 |  | showEventsCatalogAsc (Positive) | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.046.01 | Sort event sessions by name in ascending order on the Event Catalog Page (valid visitor and event name) - multiple events returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.046.02 | Sort event sessions by name in ascending order on the Event Catalog Page (valid visitor and invalid eventname) - one event session returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.046.03 | Sort event sessions by name in ascending order on the Event Catalog Page (valid visitor and invalid eventname) - no event sessions returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
1.09 |  | showEventsCatalogDesc (Positive) | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.048.01 | Sort event sessions by name in descending order on the Event Catalog Page (valid visitor and event name) - multiple events returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.048.02 | Sort event sessions by name in descending order on the Event Catalog Page (valid visitor and invalid eventname) - one event session returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.048.03 | Sort event sessions by name in descending order on the Event Catalog Page (valid visitor and invalid eventname) - no event sessions returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
1.1 |  | searchEventsByName (Positive) | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.050.01 | Attempt to search for an event session by name on the Festival Portal Page (valid visitor and event name) - multiple events returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.050.02 | Attempt to search for an event session by name on the Festival Portal Page (valid visitor and valid eventname) - one event session returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.050.03 | Attempt to search for an event session by name on the Festival Portal Page (valid visitor and invalid eventname) - no event sessions returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
1.11 |  | showEventsAsc (Positive) | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.052.01 | Sort event sessions by name in ascending order on the Festival Portal Page (valid visitor and event name) - multiple events returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.052.02 | Sort event sessions by name in ascending order on the Festival Portal Page (valid visitor and invalid eventname) - one event session returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.052.03 | Sort event sessions by name in ascending order on the Festival Portal Page (valid visitor and invalid eventname) - no event sessions returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
1.12 |  | showEventsDesc (Positive) | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.054.01 | Sort event sessions by name in descending order on the Festival Portal Page (valid visitor and event name) - multiple events returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.054.02 | Sort event sessions by name in descending order on the Festival Portal Page (valid visitor and invalid eventname) - one event session returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.054.03 | Sort event sessions by name in descending order on the Festival Portal Page (valid visitor and invalid eventname) - no event sessions returned | FERS.AT.AP331.S.006 | FERS.AT.AP331.S.006_UT.java | [64 empty] | Not Started | Not Started | Not Started
2 |  | Error Tests (Negative Outcomes) | [66 empty] | Not Started | Not Started | Not Started
2.1 |  | Register New Visitor - Negative | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.031.01 | Attempt to create a new visitor (visitor already exists in system) | FERS.AT.AP331.S.007 | FERS.AT.AP331.S.007_UT.java | [64 empty] | Not Started | Not Started | Not Started
2.2 |  | Visitor Login - Negative | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.034.01 | Attempt to find visitor using login credentials (invalid username) | FERS.AT.AP331.S.008 | FERS.AT.AP331.S.008_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.034.02 | Attempt to find visitor using login credentials (valid username, invalid password) | FERS.AT.AP331.S.008 | FERS.AT.AP331.S.008_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.034.03 | Attempt to find visitor using login credentials (empty Values for username and password) | FERS.AT.AP331.S.008 | FERS.AT.AP331.S.008_UT.java | [64 empty] | Not Started | Not Started | Not Started
2.3 |  | Update Visitor Information - Negative | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.040.01 | Attempt to update visitor information (visitor DOES NOT exist in system) | FERS.AT.AP331.S.009 | FERS.AT.AP331.S.009_UT.java | [64 empty] | Not Started | Not Started | Not Started
2.4 |  | Register for Event - Negative | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.037.01 | Attempt to register visitor for an event session (valid visitor and event session, registered for event session) | FERS.AT.AP331.S.010 | FERS.AT.AP331.S.010_UT.java | [64 empty] | Not Started | Not Started | Not Started
3 |  | Exception Tests (Outcomes that throw Exceptions) | [66 empty] | Not Started | Not Started | Not Started
3.1 |  | Register New Visitor - Exception | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.032.01 | Attempt to create a new visitor (missing Request object) | FERS.AT.AP331.S.011 | FERS.AT.AP331.S.011_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.032.02 | Attempt to create a new visitor (missing Reponse object) | FERS.AT.AP331.S.011 | FERS.AT.AP331.S.011_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.032.03 | Attempt to create a new visitor (missing objects) | FERS.AT.AP331.S.011 | FERS.AT.AP331.S.011_UT.java | [64 empty] | Not Started | Not Started | Not Started
3.2 |  | Visitor Login - Exception | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.035.01 | Attempt to find visitor using login credentials (missing object) | FERS.AT.AP331.S.012 | FERS.AT.AP331.S.012_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.035.02 | Attempt to find visitor using login credentials (missing object) | FERS.AT.AP331.S.012 | FERS.AT.AP331.S.012_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.035.03 | Attempt to find visitor using login credentials (missing objects) | FERS.AT.AP331.S.012 | FERS.AT.AP331.S.012_UT.java | [64 empty] | Not Started | Not Started | Not Started
3.3 |  | Update Visitor Information - Exception | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.041.01 | Attempt to update visitor information (missing Visitor attribute) | FERS.AT.AP331.S.013 | FERS.AT.AP331.S.013_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.041.02 | Attempt to update visitor information (missing request object) | FERS.AT.AP331.S.013 | FERS.AT.AP331.S.013_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.041.03 | Attempt to update visitor information (missing response object) | FERS.AT.AP331.S.013 | FERS.AT.AP331.S.013_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.041.04 | Attempt to update visitor information (missing objects) | FERS.AT.AP331.S.013 | FERS.AT.AP331.S.013_UT.java | [64 empty] | Not Started | Not Started | Not Started
3.4 |  | Register for Event - Exception | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.038.01 | Attempt to register visitor for an event (missing Visitor attribute) | FERS.AT.AP331.S.014 | FERS.AT.AP331.S.014_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.038.02 | Attempt to register visitor for an event session (missing event sessionID parameter) | FERS.AT.AP331.S.014 | FERS.AT.AP331.S.014_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.038.03 | Attempt to register visitor for an event (missing request object) | FERS.AT.AP331.S.014 | FERS.AT.AP331.S.014_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.038.04 | Attempt to register visitor for an event (missing response object) | FERS.AT.AP331.S.014 | FERS.AT.AP331.S.014_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.038.05 | Attempt to register visitor for an event (missing request and response object) | FERS.AT.AP331.S.014 | FERS.AT.AP331.S.014_UT.java | [64 empty] | Not Started | Not Started | Not Started
3.5 |  | Unregister for Event - Exception | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.043.01 | Attempt to unregister visitor from an event session (valid visitor and event session, not registered for event session) | FERS.AT.AP331.S.015 | FERS.AT.AP331.S.015_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.043.02 | Attempt to unregister visitor from an event session (missing request object) | FERS.AT.AP331.S.015 | FERS.AT.AP331.S.015_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.043.03 | Attempt to unregister visitor from an event session (missing response object) | FERS.AT.AP331.S.015 | FERS.AT.AP331.S.015_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.043.04 | Attempt to unregister visitor from an event session (missing objects) | FERS.AT.AP331.S.015 | FERS.AT.AP331.S.015_UT.java | [64 empty] | Not Started | Not Started | Not Started
3.6 |  | Show All Events - Exception | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.029.01 | See all available events for the visitor(null request object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.029.02 | See all available events for the visitor(null response object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.029.03 | See all available events for the visitor(both objects are null ) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
3.7 |  | searchEventsByNameCatalog (Exception) | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.045.01 | Attempt to search for an event session by name on the Festival Portal Page (missing Visitor attribute) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.045.02 | Attempt to search for an event session by name on the Festival Portal Page (missing request object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.045.03 | Attempt to search for an event session by name on the Festival Portal Page (missing response object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
3.8 |  | showEventsCatalogAsc (Exception) | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.047.01 | Sort event sessions by name in ascending order on the Festival Portal Page (missing Visitor attribute) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.047.02 | Sort event sessions by name in ascending order on the Festival Portal Page (missing request object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.047.03 | Sort event sessions by name in ascending order on the Festival Portal Page (missing response object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
3.9 |  | showEventsCatalogDesc (Exception) | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.049.01 | Sort event sessions by name in descending order on the Festival Portal Page (missing Visitor attribute) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.049.02 | Sort event sessions by name in descending order on the Festival Portal Page (missing request object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.049.03 | Sort event sessions by name in descending order on the Festival Portal Page (missing response object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
3.1 |  | searchEventsByName (Exception) | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.051.01 | Attempt to search for an event session by name on the Festival Portal Page (missing Visitor attribute) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.051.02 | Attempt to search for an event session by name on the Festival Portal Page (missing request object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.051.03 | Attempt to search for an event session by name on the Festival Portal Page (missing response object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
3.11 |  | showEventsAsc (Exception) | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.053.01 | Sort event sessions by name in ascending order on the Festival Portal Page (missing Visitor attribute) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.053.02 | Sort event sessions by name in ascending order on the Festival Portal Page (missing request object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.053.03 | Sort event sessions by name in ascending order on the Festival Portal Page (missing response object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
3.12 |  | showEventsDesc (Exception) | [66 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.055.01 | Sort event sessions by name in descending order on the Festival Portal Page (missing Visitor attribute) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.055.02 | Sort event sessions by name in descending order on the Festival Portal Page (missing request object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
| FERS.AT.AP331.TS.055.03 | Sort event sessions by name in descending order on the Festival Portal Page (missing response object) | FERS.AT.AP331.S.016 | FERS.AT.AP331.S.016_UT.java | [64 empty] | Not Started | Not Started | Not Started
END OF TEST CYCLE CONTROL SHEET